## Sheet1
Project | Task Name | Start Date | End Date | Status | Assigned To | Cost | Budget
Maintain Support Systems | HR software upgrades | 2008-01-01 | 2008-12-31 | Open | Pam King | 8000 | 7000
Maintain Support Systems | Apply Billing System updates | 2008-01-01 | 2008-12-31 | Open | Russ Sanders | 5000 | 7000
Maintain Support Systems | Investigate new Virus Protection software | 2008-02-15 | 2008-03-23 | Closed | Pam King | 1700 | 1500
Maintain Support Systems | Arrange for holiday coverage | 2008-01-10 | 2008-01-12 | Closed | Al Bines | 300 | 500
Email Integration | Complete plan | 2008-02-08 | 2008-02-14 | Closed | Mark Nile | 500 | 750
Email Integration | Check software licenses | 2008-02-12 | 2008-02-13 | Closed | Mark Nile | 200 | 200
Email Integration | Get RFPs for new server | 2008-02-19 | 2008-05-03 | Closed | Mark Nile | 4000 | 1000
Email Integration | Purchase backup server | 2008-05-12 | 2008-07-07 | Closed | Al Bines | 3200 | 3000
APEX Environment Configuration | Identify server requirements | 2008-02-19 | 2008-02-20 | Closed | John Watson | 100 | 200
APEX Environment Configuration | Specify security authentication scheme(s) | 2008-02-20 | 2008-02-22 | Closed | Scott Spencer | 200 | 300
APEX Environment Configuration | Determine Web listener configuration(s) | 2008-02-20 | 2008-02-20 | Closed | James Cassidy | 100 | 100
APEX Environment Configuration | Select servers for Development, Test, Production | 2008-02-21 | 2008-02-24 | Closed | Al Bines | 200 | 600
APEX Environment Configuration | Run installation | 2008-02-29 | 2008-02-29 | Closed | John Watson | 100 | 100
APEX Environment Configuration | Configure Workspace provisioning | 2008-02-29 | 2008-02-29 | Closed | Scott Spencer | 100 | 100
APEX Environment Configuration | Create pilot workspace | 2008-02-29 | 2008-02-29 | Closed | Scott Spencer | 100 | 100
APEX Environment Configuration | Integrate authentication schemes | 2008-03-01 | 2008-03-05 | Closed | Scott Spencer | 250 | 500
Train Developers in APEX | Create training workspace | 2008-03-01 | 2008-03-01 | Closed | James Cassidy | 100 | 100
Train Developers in APEX | Publish links to self-study courses | 2008-03-01 | 2008-03-01 | Closed | John Watson | 100 | 100
Train Developers in APEX | Publish development standards | 2008-03-01 | 2008-05-01 | On-Hold | John Watson | 1000 | 2000
Convert Excel Spreadsheet | Collect mission-critical spreadsheets | 2008-03-15 | 2008-11-15 | Open | Pam King | 2500 | 4000
Convert Excel Spreadsheet | Create APEX applications from spreadsheets | 2008-03-20 | 2008-11-30 | Open | James Cassidy | 6000 | 10000
Convert Excel Spreadsheet | Send links to previous spreadsheet owners | 2008-03-25 | 2008-12-05 | Open | Mark Nile | 1000 | 1500
Convert Excel Spreadsheet | Lock spreadsheets | 2008-03-25 | 2008-12-05 | Open | Pam King | 1000 | 1500
Load Packaged Applications | Identify point solutions required | 2008-04-03 | 2008-04-05 | Closed | John Watson | 200 | 300
Load Packaged Applications | Install in development | 2008-04-07 | 2008-04-07 | Closed | John Watson | 100 | 100
Load Packaged Applications | Customize solutions | 2008-04-08 | 2008-10-01 | Open | John Watson | 5500 | 4000
Load Packaged Applications | Implement in Production | 2008-04-10 | 2008-10-05 | Open | John Watson | 2000 | 1500
Load Packaged Applications | Train developers / users | 2008-04-10 | 2008-10-25 | Open | John Watson | 10000 | 8000
Upgrade to Oracle 11g | Identify downtime window | 2008-04-24 | 2008-04-24 | Closed | Russ Saunders | 100 | 100
Upgrade to Oracle 11g | Shutdown servers | 2008-04-26 | 2008-04-26 | Closed | Russ Saunders | 100 | 100
Upgrade to Oracle 11g | Perform upgrades | 2008-04-26 | 2008-04-27 | Closed | Russ Saunders | 300 | 200
Upgrade to Oracle 11g | Review log files | 2008-04-27 | 2008-04-27 | Closed | Russ Saunders | 100 | 100
Upgrade to Oracle 11g | Start servers | 2008-04-27 | 2008-04-27 | Closed | Russ Saunders | 100 | 100
Migrate from SQL Server | Obtain SQL Server credentials | 2008-05-03 | 2008-05-15 | Pending | James Cassidy | 0 | 500
Migrate from SQL Server | Identify integration points | 2008-05-16 | 2008-06-28 | Pending | Mark Nile | 0 | 2000
Migrate from SQL Server | Map data usage | 2008-05-20 | 2008-08-03 | Pending | Mark Nile | 0 | 8000
Migrate from SQL Server | Create DB Connection to Oracle | 2008-05-16 | 2008-05-16 | Pending | Scott Spencer | 0 | 100
Migrate from SQL Server | Migrate table structures | 2008-05-24 | 2008-08-10 | Pending | John Watson | 0 | 2500
Migrate from SQL Server | Import data | 2008-05-25 | 2008-08-13 | Pending | John Watson | 0 | 1000
Migrate from SQL Server | Convert processes | 2008-06-02 | 2008-09-01 | Pending | Pam King | 0 | 3000
Migrate from SQL Server | Reimplement integration using Oracle | 2008-06-03 | 2008-09-04 | Pending | Mark Nile | 0 | 1500
Migrate from SQL Server | Notify users | 2008-06-06 | 2008-09-09 | Pending | Mark Nile | 0 | 200
Migrate from SQL Server | Decommission SQL Server | 2008-07-01 | 2008-09-30 | Pending | Al Bines | 0 | 500
Employee Satisfaction Survey | Complete questionaire | 2008-05-18 | 2008-06-01 | On-Hold | Irene Jones | 1200 | 800
Employee Satisfaction Survey | Review with legal | 2008-06-02 | 2008-06-03 | On-Hold | Irene Jones | 200 | 400
Employee Satisfaction Survey | Plan rollout schedule | 2008-06-06 | 2008-06-08 | On-Hold | Irene Jones | 200 | 200
Discussion Forum | Identify owners | 2008-06-19 | 2008-06-22 | Closed | Hank Davis | 200 | 300
Discussion Forum | Install APEX application on internet server | 2008-06-23 | 2008-06-23 | Closed | Hank Davis | 100 | 100
Discussion Forum | Monitor participation | 2008-07-01 | 2008-10-31 | Closed | Hank Davis | 3000 | 1500
Bug Tracker | Implement bug trascking software | 2008-07-02 | 2008-07-02 | Closed | Myra Sutcliff | 100 | 100
Bug Tracker | Review automated testing tools | 2008-07-02 | 2008-08-01 | Closed | Myra Sutcliff | 1000 | 1500
Bug Tracker | Document quality assurance proceedures | 2008-08-05 | 2008-09-19 | Closed | Myra Sutcliff | 3500 | 4000
Bug Tracker | Train developers on tracking bugs | 2008-09-20 | 2008-10-10 | Open | Myra Sutcliff | 0 | 4000
Bug Tracker | Measure effectiveness of improved QA | 2008-10-01 | 2009-01-01 | Pending | Myra Sutcliff | 0 | 1500
Migrate Access Application | Identify pilot Access applications | 2008-07-10 | 2008-07-12 | Closed | Mark Nile | 300 | 500
Migrate Access Application | Migrate pilot applications to APEX | 2008-07-12 | 2008-07-17 | Closed | Mark Nile | 500 | 500
Migrate Access Application | Post-migration review | 2008-07-20 | 2008-07-20 | Closed | Mark Nile | 100 | 100
Migrate Access Application | Plan migration schedule | 2008-07-21 | 2008-07-24 | Closed | Mark Nile | 300 | 200
Migrate Access Application | Migrate Access applicaitions | 2008-08-01 | 2008-12-18 | Open | Mark Nile | 6000 | 18000
Migrate Access Application | User acceptance testing | 2008-08-15 | 2008-12-29 | Open | Mark Nile | 1500 | 6000
Migrate Access Application | End-user Training | 2009-01-03 | 2009-03-05 | Pending | John Watson | 0 | 2000
Softwatre Projects Tracking | Customize Software Projects software | 2008-07-15 | 2008-07-20 | Closed | Tom Suess | 600 | 1000
Softwatre Projects Tracking | Enter base data (Projects, Milestones, etc.) | 2008-07-23 | 2008-07-24 | Closed | Tom Suess | 200 | 200
Softwatre Projects Tracking | Load current tasks and enhancements | 2008-07-25 | 2008-08-02 | Closed | Tom Suess | 400 | 500
Softwatre Projects Tracking | Conduct project kickoff meeting | 2008-08-05 | 2008-08-05 | Closed | Pam King | 100 | 100
Public Website | Determine host server | 2008-08-06 | 2008-08-07 | Closed | Tiger Scott | 200 | 200
Public Website | Check software licenses | 2008-08-07 | 2008-08-07 | Closed | Tom Suess | 100 | 100
Public Website | Purchase additional software licenses, if needed | 2008-08-10 | 2008-09-01 | On-Hold | Al Bines | 300 | 1000
Public Website | Develop web pages | 2008-08-10 | 2008-09-15 | On-Hold | Tiger Scott | 800 | 2000
Public Website | Plan rollout schedule | 2008-09-17 | 2008-09-17 | On-Hold | Tom Suess | 0 | 100
Forms Conversion | Identify pilot Oracle Forms applications | 2008-09-01 | 2008-09-02 | Closed | Scott Spencer | 200 | 200
Forms Conversion | Migrate pilot Forms to APEX | 2008-09-04 | 2008-09-11 | Closed | Scott Spencer | 600 | 500
Forms Conversion | Post-migration review | 2008-09-12 | 2008-09-12 | Closed | Pam King | 100 | 100
Forms Conversion | Plan migration schedule | 2008-09-15 | 2008-09-15 | Closed | Pam King | 100 | 100
Forms Conversion | Migrate Oracle Forms | 2008-09-16 | 2009-02-04 | Open | Tiger Scott | 300 | 12000
Forms Conversion | Test migrated applications | 2008-10-01 | 2008-02-10 | Pending | Russ Saunders | 0 | 6000
Forms Conversion | User acceptance testing | 2008-10-16 | 2009-02-20 | Pending | Al Bines | 0 | 2500
Forms Conversion | End-user Training | 2008-10-20 | 2009-03-01 | Pending | John Watson | 0 | 2500
Forms Conversion | Rollout migrated Forms in APEX | 2008-10-20 | 2009-03-03 | Pending | Scott Spencer | 0 | 500